## Sheet1
Project Leader: |  | Nguyễn Hoàng Đức Duy | Project: Xây dựng web book tour du lịch | [9 empty] | Date: 21/3/2022
Project Objective: Xây dựng một web để đặt tour du lịch
Major Tasks |  |  | Project Completed By: 27/02/2022 | [9 empty] | Owner/Priority
|  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9
1 | Review Node.js, Express.js, MongoDB, Mongoose | [11 empty] | A | B | B | B
2 | Design database schema | [11 empty] | A
3 | SRS | [12 empty] | B | A | B
4 | CRUD | [11 empty] | A
5 | Filter | [11 empty] | A
6 | Sort | [12 empty] | A
7 | Limit fileds | [14 empty] | A
8 | Pagination | [13 empty] | A
9 | Login | [12 empty] | A
10 | Sign up | [13 empty] | A
11 | Forgot password | [11 empty] | A
12 | Reset password | [11 empty] | A
13 | Update password | [13 empty] | A
14 | Update user info | [12 empty] | A
15 | Delete user | [14 empty] | A
16 | Protect route | [11 empty] | A
17 | Authorization | [11 empty] | A
18 | Review CRUD | [11 empty] | A
19 | API docs | [11 empty] | A
20 | Handle errors | [11 empty] | A | B | B | B
21 | Security | [11 empty] | A | B | B | B
22 | Render data inttemplate | [11 empty] | A | B | B | B
23 | Payments, Email, File uploads | [11 empty] | A | B | B | B
|  |  | 21/3/2022 | 28/3/2022 | 2022-04-04 | 2022-04-11 | 18/4/2022 | 25/4/2022 | 2022-05-02 | 2022-05-09 | 16/5/2022 | 23/5/2022 | Đức Duy | Thanh Hoàng | Thanh Tấn | Văn Dũng