## Sheet1
Project Leader: |  | Nguyễn Hoàng Đức Duy | Project: Xây dựng web book tour du lịch | [10 empty] | Date: 21/3/2022
Project Objective: Xây dựng một web để đặt tour du lịch
Major Tasks |  |  | Project Completed By: 27/02/2022 | [10 empty] | Owner/Priority
|  |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11
1 | Review Node.js, Express.js, MongoDB, Mongoose | [12 empty] | A | B | B | B
2 | Design database schema | [12 empty] | A
3 | SRS | [13 empty] | B | A | B
4 | Tour API
| 1. CRUD | [12 empty] | A | B
| 2. Filter | [12 empty] | A | B
| 3. Sort | [12 empty] | A |  | B
| 4. Limit fileds | [12 empty] | A |  |  | B
| 5. Pagination | [12 empty] | A |  |  | B
5 | User API
| 1. Login | [12 empty] | A | B
| 2. Sign up | [12 empty] | A |  |  | B
| 3. Forgot password | [12 empty] | A |  | B
| 4. Reset password | [12 empty] | A |  | B
| 5. Update password | [12 empty] | A | B
| 6. Update user info | [12 empty] | A |  |  | B
| 7. Delete user | [12 empty] | A | B
| 8. Protect route | [12 empty] | A | B
| 9. Authorization | [12 empty] | A |  | B
6 | Review CRUD | [12 empty] | A |  | B
7 | API docs | [12 empty] | A |  |  | B
8 | Handle errors | [12 empty] | A | B | B | B
9 | Security | [12 empty] | A | B | B | B
10 | Render data inttemplate
| 1. Base, header, footer | [12 empty] | A |  | B
| 2. Account | [12 empty] | A | B
| 3. Error | [12 empty] | A | B
| 4. Login, sign up | [12 empty] | A |  | B
| 5. Home page | [12 empty] | A |  |  | B
| 6. Tour details | [12 empty] | A |  |  | B
11 | Payments, Email, File uploads | [12 empty] | A | B | B | B
|  |  | 21/3/2022 | 28/3/2022 | 2022-04-04 | 2022-04-11 | 18/4/2022 | 25/4/2022 | 2022-05-02 | 2022-05-09 | 16/5/2022 | 23/5/2022 | 30/5/2022 | Đức Duy | Thanh Hoàng | Thanh Tấn | Văn Dũng